## How to use
Feature priorities — Gardening Companion
1. Open the "Priorities" sheet.
2. In the yellow "Your priority" column, pick one value for each row:
• MVP — needed in the first usable version
• Good to have — after the MVP, still planned
• Future improvement — later, maybe
3. "Suggested" is Claude's suggestion, for reference only. Change anything.
4. Use "Your notes" for comments or changes to a row.
5. Only edit the yellow columns. The "Summary" sheet counts your choices automatically.
6. Rows marked "Decided earlier: not in MVP" were already agreed as later — change them if you've changed your mind.
7. When finished, export as Excel (Share → Export → Excel) and send the file back in the chat.
Example: row "Plot boundary on satellite map" → Your priority: MVP → Your notes: "Tap corners is enough"

## Priorities
ID | Feature | Sub-feature | What it means | Your priority | Suggested | Your notes | Info
0.1 | Foundations | Sign-in and accounts | Entra External ID sign-in (email, Apple, Google); every record belongs to a user |  | MVP |  | Needed by almost everything
0.2 | Foundations | Portuguese and English | Whole app and content in pt-PT and English |  | MVP |  | Decided earlier: first version
0.3 | Foundations | Offline sync | Work offline and sync later; you resolve conflicts yourself |  | MVP |  | Needed by journal, tasks, map
0.4 | Foundations | Activity log | Permanent history of everything done; base for roadmap, journal and AI |  | MVP |  | Needed by roadmap, journal and AI
0.5 | Foundations | Knowledge base pipeline | Crops, guides and tools kept in git (PT/EN), published to the app and AI |  | MVP |  | Needed by calendar, guides and AI
0.6 | Foundations | Account deletion and data export | Required by Apple and Google for apps with accounts |  | MVP |  | Store requirement
0.7 | Foundations | Android app | Port each stable iOS milestone to Android |  | Good to have |  | Decided earlier: iOS first
3.1.1 | Project roadmap | Next actions (rules) | Fixed agronomy rules work out the next actions per zone, with safety limits |  | MVP
3.1.2 | Project roadmap | Next actions (AI) | AI ranks and adapts next actions, explains why |  | Good to have
3.1.3 | Project roadmap | Per-zone stages | Each zone has its own stage, worked out from its state |  | MVP
3.1.4 | Project roadmap | Starting point | Setup asks what already exists so you don't start from zero |  | MVP
3.1.5 | Project roadmap | Season-aware timing | Actions scheduled in their ideal time window for your climate |  | MVP
3.1.6 | Project roadmap | Time and cost estimates | Rough time and cost for each action |  | Good to have
3.1.7 | Project roadmap | Deviation handling | Mark actions as done differently, skipped, not possible or a problem; plan adapts |  | MVP
3.1.8 | Project roadmap | Content freshness review | AI proposes updates to outdated content; you review before publishing |  | Future improvement
3.3.1 | Plot mapping | Plot boundary on satellite map | Draw the plot by tapping corners |  | MVP
3.3.2 | Plot mapping | Walk boundary with GPS | Walk around the plot to draw it |  | Good to have
3.3.3 | Plot mapping | Zones and beds | Draw zones and beds, or enter exact dimensions |  | MVP
3.3.4 | Plot mapping | Points of interest | Water, electricity, access, buildings, trees with heights |  | MVP |  | Irrigation needs water sources
3.3.5 | Plot mapping | Area, sun and slope | Calculated automatically from the map and elevation data |  | MVP
3.3.6 | Plot mapping | Soil type estimate | Estimated from global soil maps (SoilGrids), no tests |  | Good to have
3.3.7 | Plot mapping | Shade estimation | Shade from trees and buildings over the day and year, plus observed shade |  | Good to have
3.3.8 | Plot mapping | Prevailing wind | Wind direction from weather data, windbreak suggestions |  | Future improvement
3.3.9 | Plot mapping | Layout designer | Beds with real dimensions, paths, row direction |  | MVP
3.3.10 | Plot mapping | Measuring tool | Measure distances on the map (e.g. pipe length) |  | Good to have
3.3.11 | Plot mapping | Layout history | Each season's layout kept as a version |  | Good to have |  | Rotation planner needs it
3.3.12 | Plot mapping | Several plots per user | e.g. a backyard and a separate field |  | Future improvement |  | Decided earlier: not in MVP
3.4.1 | Site assessment | AI photo assessment | Vegetation to clear, problem plants, trees to keep, obstacles, terrain, water problems, infrastructure |  | MVP
3.4.2 | Site assessment | Wildlife pressure | Signs of rabbits, wild boar, birds, moles; fencing advice |  | Good to have
3.4.3 | Site assessment | Fixed photo spots | Guided photos from the same spots for before-and-after |  | Good to have
3.4.4 | Site assessment | Walk-around video | Film a zone; the app picks frames for the AI |  | Future improvement
3.4.5 | Site assessment | Equipment advice | Buy, rent or borrow big equipment (follows "always own") |  | Good to have
3.4.6 | Site assessment | Re-assessments | Repeat the assessment to track progress |  | Good to have
3.5.1 | Planting calendar | Climate-based windows | Sow, plant-out and harvest windows from local climate history |  | MVP
3.5.2 | Planting calendar | Too-hot windows | Avoid heat for crops that bolt or stop fruiting |  | MVP |  | Critical in Alentejo
3.5.3 | Planting calendar | Month view and "This week" | Calendar views |  | MVP
3.5.4 | Planting calendar | Forecast adjustment | Windows shifted by the weather forecast |  | Good to have
3.5.5 | Planting calendar | Zone fit | What can be planted now in each zone (sun and shade) |  | Good to have
3.5.6 | Planting calendar | Varieties | Early and late varieties with different timing |  | Good to have
3.5.7 | Planting calendar | Day length | Varieties suited to your latitude (e.g. short-day onions) |  | Good to have
3.5.8 | Planting calendar | Heat-based harvest estimates | Harvest dates from heat received since sowing |  | Good to have
3.5.9 | Planting calendar | Staggered sowing reminders | e.g. lettuce every 2–3 weeks |  | Good to have
3.5.10 | Planting calendar | Export to phone calendar | Add sowing and harvest dates to iOS Calendar |  | Future improvement
3.6.1 | Choosing your crops | Pick crops | Choose crops with variety, priority and quantity |  | MVP
3.6.2 | Choosing your crops | Ranked suggestions | Crops ranked by fit for your location, with reasons |  | MVP
3.6.3 | Choosing your crops | Poor-fit warnings | Warns about a bad crop or timing, never blocks |  | MVP
3.6.4 | Choosing your crops | How much to plant | Number of plants and space from the quantity you want |  | Good to have
3.6.5 | Choosing your crops | AI explanation | Personalised AI explanation of the suggestions |  | Future improvement
3.7.1 | Guides | Step-by-step guides with sources | PT and EN guides citing sources, with review dates |  | MVP
3.7.2 | Guides | Standard step layout | What to do, illustration, tools, time, safety, mistakes, "done right" check |  | MVP
3.7.3 | Guides | Technique guides | Clearing, beds, drip irrigation, mulching, compost, sowing, planting out… |  | MVP
3.7.4 | Guides | Crop guides | Each crop from sowing to harvest |  | MVP
3.7.5 | Guides | Problem guides | Pests and diseases, organic methods first |  | Good to have
3.7.6 | Guides | Quantities from your numbers | e.g. compost for your exact bed size |  | Good to have
3.7.7 | Guides | Doing mode with read-aloud | Big text, one step at a time, spoken steps |  | Good to have
3.7.8 | Guides | Ask AI about a step | Ask the AI about the step you're on |  | Good to have
3.7.9 | Guides | Photo check of your work | AI checks a photo of the finished step |  | Future improvement
3.7.10 | Guides | Unclear-step feedback | Flag unclear steps for content review |  | Future improvement
3.7.11 | Guides | Offline download | Text and images available offline |  | MVP
3.7.12 | Guides | Selected videos | Links to good videos, with a broken-link check |  | Good to have
3.7.13 | Guides | AI illustrations | gpt-image illustrations plus diagrams, reviewed by you |  | Good to have
3.7.14 | Guides | AI-generated video or animations | Generated once per guide and reviewed |  | Future improvement |  | Decided earlier: not in MVP
3.8.1 | Journal and timeline | Entries with photos and notes | Log what you did per zone, bed or planting |  | MVP
3.8.2 | Journal and timeline | Quick and bulk logging | One tap; several beds at once |  | MVP
3.8.3 | Journal and timeline | Voice notes | Dictate notes in the field |  | Good to have
3.8.4 | Journal and timeline | Automatic entries | Completing actions, tasks or guide steps logs them |  | MVP
3.8.5 | Journal and timeline | Weather on each day | Day's rain and temperatures attached automatically |  | Good to have
3.8.6 | Journal and timeline | Change the date | Log things after the fact |  | MVP
3.8.7 | Journal and timeline | Timeline views | History for a zone, bed or planting |  | Good to have
3.8.8 | Journal and timeline | Photo time-lapse | From the fixed photo spots |  | Future improvement
3.8.9 | Journal and timeline | Harvest log | Weight or count per crop, compared with expected |  | MVP
3.8.10 | Journal and timeline | Harvest value | Estimated value using prices you enter |  | Future improvement
3.8.11 | Journal and timeline | Search and filters | Find past entries |  | Good to have
3.8.12 | Journal and timeline | Export CSV/PDF | Export your journal |  | Future improvement
3.9.1 | Tasks and reminders | Tasks from all sources | Roadmap, calendar, care, weather, AI and your own |  | MVP
3.9.2 | Tasks and reminders | Task details | Date range, time estimate, priority, guide link |  | MVP
3.9.3 | Tasks and reminders | Tools check | Warns if a tool you need is missing |  | Good to have
3.9.4 | Tasks and reminders | Task outcomes | Done, skipped or couldn't do (with reason) |  | MVP
3.9.5 | Tasks and reminders | Today, Week and zone views | Task list views |  | MVP
3.9.6 | Tasks and reminders | Weekend planner | Pick the best tasks for the hours you have |  | Good to have
3.9.7 | Tasks and reminders | Weather-aware rescheduling | Skip watering before rain, water early in heat… |  | Good to have
3.9.8 | Tasks and reminders | Repeating tasks | e.g. weekly feeding |  | MVP
3.9.9 | Tasks and reminders | Missed-task alternatives | Roadmap suggests an alternative when a window is missed |  | Good to have
3.9.10 | Tasks and reminders | On-phone reminders | Reminders that work offline |  | MVP
3.9.11 | Tasks and reminders | Morning summary | One daily notification instead of many |  | Good to have
3.9.12 | Tasks and reminders | Quiet hours | No notifications at set times |  | Good to have
3.9.13 | Tasks and reminders | Share tasks with family | Helpers see and do tasks |  | Future improvement |  | Decided earlier: not in MVP
3.10.1 | Tools | My tools with reference images | List of owned tools, each with an image to recognise it |  | MVP
3.10.2 | Tools | Own photo of a tool | Replace the reference image with your photo |  | Future improvement
3.10.3 | Tools | Tools needed per action | Actions, tasks and guides list their tools |  | MVP
3.10.4 | Tools | "Tools to get" list | Missing tools ordered by when needed |  | MVP
3.10.5 | Tools | "Always own" setting | Default to buy; hide rent and borrow |  | MVP |  | You use this setting
3.10.6 | Tools | Starter toolkit | Recommended set for your plot: essential vs nice to have |  | MVP
3.10.7 | Tools | Buy/rent/borrow advice | For big equipment (hidden when "always own" is on) |  | Future improvement
3.10.8 | Tools | Maintenance reminders | Sharpen, clean, store before frost |  | Good to have
3.10.9 | Tools | Shop links and affiliates | Commercial idea |  | Future improvement |  | Decided earlier: not in MVP
3.11.1 | Irrigation planner | Water sources and bucket test | Sources from the map; measure flow rate |  | MVP
3.11.2 | Irrigation planner | Method per bed | Drip line, drippers, soaker hose or sprinklers |  | MVP
3.11.3 | Irrigation planner | System layout on map | Main pipe, branches, drip lines per bed |  | MVP
3.11.4 | Irrigation planner | Flow check and sectors | Split into sectors if flow is too low; filter, regulator, backflow |  | MVP
3.11.5 | Irrigation planner | Parts list | For information only |  | MVP
3.11.6 | Irrigation planner | Watering schedule | Run times from crop and season guidance, adjusted by weather; creates tasks |  | MVP
3.11.7 | Irrigation planner | Hand-watering guidance | Before a system is installed |  | MVP
3.11.8 | Irrigation planner | Mulching advice | Reduce water use |  | Good to have
3.11.9 | Irrigation planner | Rainwater harvesting estimate | Roof area × rainfall, tank size |  | Future improvement
3.11.10 | Irrigation planner | Seasonal reminders | Flush lines, clean filters, drain before frost |  | Good to have
3.11.11 | Irrigation planner | Smart controllers and sensors | Connect irrigation controllers and soil moisture sensors |  | Future improvement |  | Decided earlier: not in MVP
3.12.1 | Weather alerts | Crop-aware alerts | Frost, heat, wind, rain, hail, storms, dry spells — only when your crops are at risk |  | MVP
3.12.2 | Weather alerts | Skip-watering notices | Rain is coming |  | MVP
3.12.3 | Weather alerts | Good-conditions alerts | e.g. good day to plant out |  | Good to have
3.12.4 | Weather alerts | Actions as tasks | Each alert creates tasks with guide links |  | MVP
3.12.5 | Weather alerts | Severity and confidence | Watch vs warning; forecast confidence |  | Good to have
3.12.6 | Weather alerts | Quiet-hours override | Urgent alerts break through quiet hours |  | Good to have
3.12.7 | Weather alerts | 7-day weather screen | Forecast with gardening notes |  | MVP
3.12.8 | Weather alerts | Follow-up after event | Check plants and log damage after frost or storm |  | Good to have
3.12.9 | Weather alerts | IPMA official warnings | Portuguese official weather warnings |  | Good to have
3.12.10 | Weather alerts | Other countries' warnings | MeteoAlarm or national services |  | Future improvement |  | Decided earlier: not in MVP
3.13.1 | Plant identification | Photo identification | Top matches with confidence, PT/EN and scientific names |  | MVP
3.13.2 | Plant identification | Crop-or-weed verdict | Especially for seedlings |  | MVP
3.13.3 | Plant identification | Context for accuracy | Uses location, season and what's planted in the bed |  | MVP
3.13.4 | Plant identification | Several photos | Leaf, flower, whole plant |  | Good to have
3.13.5 | Plant identification | Invasive and toxic flags | Warnings only; never says a wild plant is safe to eat |  | MVP
3.13.6 | Plant identification | One-tap actions | Add as planting, mark as weed (removal task), keep tree |  | Good to have
3.13.7 | Plant identification | Corrections | Fix wrong results; used as context and for testing |  | Good to have
3.13.8 | Plant identification | Specialist ID service | Second opinion from a plant-ID service |  | Future improvement |  | Decided earlier: not in MVP
3.14.1 | Pest and disease diagnosis | Photo diagnosis | Pests, diseases, nutrient problems and environmental stress |  | MVP
3.14.2 | Pest and disease diagnosis | Follow-up questions | AI asks questions when unsure |  | Good to have
3.14.3 | Pest and disease diagnosis | Treatment plans | Organic first; chemicals last, never by product name |  | MVP
3.14.4 | Pest and disease diagnosis | Treatment tasks and check-ups | Re-photograph later, before-and-after comparison |  | Good to have
3.14.5 | Pest and disease diagnosis | Spread warnings and bed flags | Warn other beds; flag soil-borne diseases for rotation |  | Good to have
3.14.6 | Pest and disease diagnosis | Disease-risk warnings | Weather-based risk, e.g. mildew |  | Good to have
3.14.7 | Pest and disease diagnosis | Seasonal scouting tasks | "Check under the cabbage leaves this week" |  | Future improvement
3.14.8 | Pest and disease diagnosis | Beneficial insects | Recognise helpful insects so you don't kill them |  | Good to have
3.15.1 | Harvest readiness | Photo verdict | Not yet, soon, ready, past its best |  | Good to have
3.15.2 | Harvest readiness | Advance notice | Harvest window approaching |  | Good to have
3.15.3 | Harvest readiness | Signs checklists | Per crop, incl. "dig one up" for root crops |  | MVP
3.15.4 | Harvest readiness | How to harvest | Technique, time of day, keep plants producing |  | MVP
3.15.5 | Harvest readiness | Weather-aware harvest timing | e.g. pick before heavy rain |  | Good to have
3.15.6 | Harvest readiness | One-tap harvest logging | Ready → harvested → quantity |  | MVP
3.15.7 | Harvest readiness | Glut warning | Peaks coming, ideas to preserve or give away |  | Future improvement
3.15.8 | Harvest readiness | Storage and preserving guides | How to store and preserve each crop |  | Good to have
3.15.9 | Harvest readiness | Seed saving | Save seeds from your crops |  | Future improvement |  | Decided earlier: not in MVP
3.16.1 | Season planner | Crops into beds | Which crop in which bed, when, how many |  | MVP
3.16.2 | Season planner | Layout inside each bed | Rows or grid with spacing |  | Good to have
3.16.3 | Season planner | Year view per bed | Gantt-style timeline, empty periods highlighted |  | Good to have
3.16.4 | Season planner | Follow-on crops | Next crop after a harvest in the same bed |  | Good to have
3.16.5 | Season planner | Cover crops | Green cover for empty beds |  | Future improvement
3.16.6 | Season planner | Crop rotation | 4-group rotation with warnings |  | MVP
3.16.7 | Season planner | Companion planting | Pairings labelled by evidence level |  | Future improvement
3.16.8 | Season planner | Space check | Warns when crops don't fit; must-haves first |  | MVP
3.16.9 | Season planner | Perennials | Asparagus, strawberries, herbs, fruit trees stay put |  | Good to have
3.16.10 | Season planner | Drag-and-drop editing | Edit with live checks |  | Good to have
3.16.11 | Season planner | Draft and active plans | Plan next season while this one runs |  | Good to have
3.16.12 | Season planner | Learning from last year | Adjust from harvest log and notes |  | Future improvement
3.16.13 | Season planner | AI goals | Optimise for most harvest, least work or least water |  | Future improvement
3.17.1 | AI assistant | Chat with garden context | Answers about your garden, citing sources, in PT/EN |  | MVP
3.17.2 | AI assistant | "Ask about this" | Ask from any bed, plant, task, guide step or alert |  | Good to have
3.17.3 | AI assistant | Voice and photo input | Speak or send photos in the chat |  | Good to have
3.17.4 | AI assistant | Hands-free voice mode | Spoken answers in the field |  | Future improvement
3.17.5 | AI assistant | Proposed actions | Creates proposals you confirm; logged and undoable |  | MVP
3.17.6 | AI assistant | Garden memory notes | Facts it learns, visible and editable |  | Good to have
3.17.7 | AI assistant | Queued offline questions | Answered when back online |  | Future improvement
3.17.8 | AI assistant | History and search | Past conversations |  | Good to have
3.17.9 | AI assistant | Answer feedback | Thumbs up or down |  | Good to have
3.18.1 | Improvement suggestions | Garden report | Weekly stats: done, harvested, weather, photos, next week |  | Good to have
3.18.2 | Improvement suggestions | AI suggestions with evidence | Reason, evidence, impact and effort |  | Good to have
3.18.3 | Improvement suggestions | Accept, dismiss, snooze | Accept becomes a proposal; dismissals aren't repeated |  | Good to have
3.18.4 | Improvement suggestions | Patterns over time | Insights across weeks and seasons |  | Future improvement
3.18.5 | Improvement suggestions | End-of-season review | Retrospective feeding next season's plan |  | Good to have
3.18.6 | Improvement suggestions | Configurable frequency | Weekly, fortnightly or monthly |  | Future improvement
3.19.1 | App-wide | "Today" home screen | Next actions, tasks, alerts, forecast, proposals |  | MVP
3.19.2 | App-wide | First-run setup | Guided flow from location to crops |  | MVP
3.19.3 | App-wide | Settings | Language, units, notifications, preferences |  | MVP
3.19.4 | App-wide | AI usage meter | See how much AI you've used |  | Good to have
3.19.5 | App-wide | Photo and location privacy | Strip GPS from photos; keep plot location private |  | MVP
3.19.6 | App-wide | Crash reporting and usage stats | See problems and anonymous usage |  | MVP
3.19.7 | App-wide | Accessibility | Larger text, VoiceOver, colour-blind-friendly colours |  | Good to have
3.19.8 | App-wide | Home screen widgets | Today's tasks and alerts |  | Future improvement |  | Decided earlier: not in MVP
3.19.9 | App-wide | Apple Watch | Quick logging from the watch |  | Future improvement |  | Decided earlier: not in MVP
3.19.10 | App-wide | Siri shortcuts | e.g. "log watering zone A" |  | Future improvement |  | Decided earlier: not in MVP
7.1 | Commercial readiness | Freemium subscriptions | App Store and Play subscriptions, tier limits |  | Future improvement |  | Only when going commercial
7.2 | Commercial readiness | Commercial data licences | Weather and other data sources for commercial use |  | Future improvement |  | Only when going commercial
7.3 | Commercial readiness | Expert review of guides | Agronomist reviews all content |  | Future improvement |  | Only when going commercial
7.4 | Commercial readiness | Commissioned illustrator | Professional illustrations |  | Future improvement |  | Only when going commercial
7.5 | Commercial readiness | Privacy policy, GDPR, store listings | Legal and store preparation |  | Future improvement |  | Only when going commercial

## Summary
Feature | MVP | Good to have | Future improvement | Not decided | Total
Foundations | 0 | 0 | 0 | 7 | 7
Project roadmap | 0 | 0 | 0 | 8 | 8
Plot mapping | 0 | 0 | 0 | 12 | 12
Site assessment | 0 | 0 | 0 | 6 | 6
Planting calendar | 0 | 0 | 0 | 10 | 10
Choosing your crops | 0 | 0 | 0 | 5 | 5
Guides | 0 | 0 | 0 | 14 | 14
Journal and timeline | 0 | 0 | 0 | 12 | 12
Tasks and reminders | 0 | 0 | 0 | 13 | 13
Tools | 0 | 0 | 0 | 9 | 9
Irrigation planner | 0 | 0 | 0 | 11 | 11
Weather alerts | 0 | 0 | 0 | 10 | 10
Plant identification | 0 | 0 | 0 | 8 | 8
Pest and disease diagnosis | 0 | 0 | 0 | 8 | 8
Harvest readiness | 0 | 0 | 0 | 9 | 9
Season planner | 0 | 0 | 0 | 13 | 13
AI assistant | 0 | 0 | 0 | 9 | 9
Improvement suggestions | 0 | 0 | 0 | 6 | 6
App-wide | 0 | 0 | 0 | 10 | 10
Commercial readiness | 0 | 0 | 0 | 5 | 5
Total | 0 | 0 | 0 | 185 | 185